{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet2"],"not_rendered":{"external_links":1,"defined_names":3,"comments":10},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet2","index":0,"n_rows":366,"n_cols":15,"rows_kept":366,"merged":[[1,0,1,14],[2,10,2,14],[6,0,14,0],[6,1,14,1],[6,2,14,2],[6,3,14,3],[6,4,14,4],[6,5,14,5],[6,11,14,11],[6,12,14,12],[6,13,14,13],[6,14,14,14],[15,0,23,0],[15,1,23,1],[15,2,23,2],[15,3,23,3],[15,4,23,4],[15,5,23,5],[15,11,23,11],[15,12,23,12],[15,13,23,13],[15,14,23,14],[24,0,32,0],[24,1,32,1],[24,2,32,2],[24,3,32,3],[24,4,32,4],[24,5,32,5],[24,11,32,11],[24,12,32,12],[24,13,32,13],[24,14,32,14],[33,0,41,0],[33,1,41,1],[33,2,41,2],[33,3,41,3],[33,4,41,4],[33,5,41,5],[33,11,41,11],[33,12,41,12],[33,13,41,13],[33,14,41,14],[42,0,50,0],[42,1,50,1],[42,2,50,2],[42,3,50,3],[42,4,50,4],[42,5,50,5],[42,11,50,11],[42,12,50,12],[42,13,50,13],[42,14,50,14],[51,0,59,0],[51,1,59,1],[51,2,59,2],[51,3,59,3],[51,4,59,4],[51,5,59,5],[51,11,59,11],[51,12,59,12],[51,13,59,13],[51,14,59,14],[60,0,68,0],[60,1,68,1],[60,2,68,2],[60,3,68,3],[60,4,68,4],[60,5,68,5],[60,11,68,11],[60,12,68,12],[60,13,68,13],[60,14,68,14],[69,0,77,0],[69,1,77,1],[69,2,77,2],[69,3,77,3],[69,4,77,4],[69,5,77,5],[69,11,77,11],[69,12,77,12],[69,13,77,13],[69,14,77,14],[78,0,86,0],[78,1,86,1],[78,2,86,2],[78,3,86,3],[78,4,86,4],[78,5,86,5],[78,11,86,11],[78,12,86,12],[78,13,86,13],[78,14,86,14],[87,0,95,0],[87,1,95,1],[87,2,95,2],[87,3,95,3],[87,4,95,4],[87,5,95,5],[87,11,95,11],[87,12,95,12],[87,13,95,13],[87,14,95,14],[96,0,104,0],[96,1,104,1],[96,2,104,2],[96,3,104,3],[96,4,104,4],[96,5,104,5],[96,11,104,11],[96,12,104,12],[96,13,104,13],[96,14,104,14],[105,0,113,0],[105,1,113,1],[105,2,113,2],[105,3,113,3],[105,4,113,4],[105,5,113,5],[105,11,113,11],[105,12,113,12],[105,13,113,13],[105,14,113,14],[114,0,122,0],[114,1,122,1],[114,2,122,2],[114,3,122,3],[114,4,122,4],[114,5,122,5],[114,11,122,11],[114,12,122,12],[114,13,122,13],[114,14,122,14],[123,0,131,0],[123,1,131,1],[123,2,131,2],[123,3,131,3],[123,4,131,4],[123,5,131,5],[123,11,131,11],[123,12,131,12],[123,13,131,13],[123,14,131,14],[132,0,140,0],[132,1,140,1],[132,2,140,2],[132,3,140,3],[132,4,140,4],[132,5,140,5],[132,11,140,11],[132,12,140,12],[132,13,140,13],[132,14,140,14],[141,0,149,0],[141,1,149,1],[141,2,149,2],[141,3,149,3],[141,4,149,4],[141,5,149,5],[141,11,149,11],[141,12,149,12],[141,13,149,13],[141,14,149,14],[150,0,158,0],[150,1,158,1],[150,2,158,2],[150,3,158,3],[150,4,158,4],[150,5,158,5],[150,11,158,11],[150,12,158,12],[150,13,158,13],[150,14,158,14],[159,0,167,0],[159,1,167,1],[159,2,167,2],[159,3,167,3],[159,4,167,4],[159,5,167,5],[159,11,167,11],[159,12,167,12],[159,13,167,13],[159,14,167,14],[168,0,176,0],[168,1,176,1],[168,2,176,2],[168,3,176,3],[168,4,176,4],[168,5,176,5],[168,11,176,11],[168,12,176,12],[168,13,176,13],[168,14,176,14],[177,0,185,0],[177,1,185,1],[177,2,185,2],[177,3,185,3],[177,4,185,4],[177,5,185,5],[177,11,185,11],[177,12,185,12],[177,13,185,13],[177,14,185,14],[186,0,194,0],[186,1,194,1],[186,2,194,2],[186,3,194,3],[186,4,194,4],[186,5,194,5],[186,11,194,11],[186,12,194,12],[186,13,194,13],[186,14,194,14],[195,0,203,0],[195,1,203,1],[195,2,203,2],[195,3,203,3],[195,4,203,4],[195,5,203,5],[195,11,203,11],[195,12,203,12],[195,13,203,13],[195,14,203,14],[204,0,212,0],[204,1,212,1],[204,2,212,2],[204,3,212,3],[204,4,212,4],[204,5,212,5],[204,11,212,11],[204,12,212,12],[204,13,212,13],[204,14,212,14],[213,0,221,0],[213,1,221,1],[213,2,221,2],[213,3,221,3],[213,4,221,4],[213,5,221,5],[213,11,221,11],[213,12,221,12],[213,13,221,13],[213,14,221,14],[222,0,230,0],[222,1,230,1],[222,2,230,2],[222,3,230,3],[222,4,230,4],[222,5,230,5],[222,11,230,11],[222,12,230,12],[222,13,230,13],[222,14,230,14],[231,0,239,0],[231,1,239,1],[231,2,239,2],[231,3,239,3],[231,4,239,4],[231,5,239,5],[231,11,239,11],[231,12,239,12],[231,13,239,13],[231,14,239,14],[240,0,248,0],[240,1,248,1],[240,2,248,2],[240,3,248,3],[240,4,248,4],[240,5,248,5],[240,11,248,11],[240,12,248,12],[240,13,248,13],[240,14,248,14],[249,0,257,0],[249,1,257,1],[249,2,257,2],[249,3,257,3],[249,4,257,4],[249,5,257,5],[249,11,257,11],[249,12,257,12],[249,13,257,13],[249,14,257,14],[258,0,266,0],[258,1,266,1],[258,2,266,2],[258,3,266,3],[258,4,266,4],[258,5,266,5],[258,11,266,11],[258,12,266,12],[258,13,266,13],[258,14,266,14],[267,0,275,0],[267,1,275,1],[267,2,275,2],[267,3,275,3],[267,4,275,4],[267,5,275,5],[267,11,275,11],[267,12,275,12],[267,13,275,13],[267,14,275,14],[276,0,284,0],[276,1,284,1],[276,2,284,2],[276,3,284,3],[276,4,284,4],[276,5,284,5],[276,11,284,11],[276,12,284,12],[276,13,284,13],[276,14,284,14],[285,0,293,0],[285,1,293,1],[285,2,293,2],[285,3,293,3],[285,4,293,4],[285,5,293,5],[285,11,293,11],[285,12,293,12],[285,13,293,13],[285,14,293,14],[294,0,302,0],[294,1,302,1],[294,2,302,2],[294,3,302,3],[294,4,302,4],[294,5,302,5],[294,11,302,11],[294,12,302,12],[294,13,302,13],[294,14,302,14],[303,0,311,0],[303,1,311,1],[303,2,311,2],[303,3,311,3],[303,4,311,4],[303,5,311,5],[303,11,311,11],[303,12,311,12],[303,13,311,13],[303,14,311,14],[312,0,320,0],[312,1,320,1],[312,2,320,2],[312,3,320,3],[312,4,320,4],[312,5,320,5],[312,11,320,11],[312,12,320,12],[312,13,320,13],[312,14,320,14],[321,0,329,0],[321,1,329,1],[321,2,329,2],[321,3,329,3],[321,4,329,4],[321,5,329,5],[321,11,329,11],[321,12,329,12],[321,13,329,13],[321,14,329,14],[330,0,338,0],[330,1,338,1],[330,2,338,2],[330,3,338,3],[330,4,338,4],[330,5,338,5],[330,11,338,11],[330,12,338,12],[330,13,338,13],[330,14,338,14],[339,0,347,0],[339,1,347,1],[339,2,347,2],[339,3,347,3],[339,4,347,4],[339,5,347,5],[339,11,347,11],[339,12,347,12],[339,13,347,13],[339,14,347,14],[348,0,356,0],[348,1,356,1],[348,2,356,2],[348,3,356,3],[348,4,356,4],[348,5,356,5],[348,11,356,11],[348,12,356,12],[348,13,356,13],[348,14,356,14],[357,0,365,0],[357,1,365,1],[357,2,365,2],[357,3,365,3],[357,4,365,4],[357,5,365,5],[357,11,365,11],[357,12,365,12],[357,13,365,13],[357,14,365,14]],"flags":["formulas_cached_only"]}
["附件2"]
["清城区2021年重点建设前期预备项目计划表"]
[{"$nulls":10},"投资单位:万元"]
["序号","项目名称","项目代码","所属行业","建设内容及规模","估算总投资","2021年主要前期工作内容","办理进展情况","责任单位","年度目标","完成时限","建设单位","申报单位","项目所在地","备注"]
["备注","1.续列项目以2021年印发计划项目名称为准；\n2.新增项目以项目立项名称为准。","一项目一代码","按重点项目行业",{"$nulls":3},"已完成；未完成；不需办理","不需办理则无需填写"]
[null,"合计（40项）",{"$nulls":3},3684855.69]
[1,"清远石角天然气分布式能源站项目","2020-441802-44-02-063044",null,"拟建设2*10万千瓦燃气-蒸汽联合循环抽凝热电机组及配套供热管网，总投资10亿元。",100000,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成","2021-12-01","石角镇","石角镇","石角镇","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"用地报批","不需办理","/","/","/"]
[{"$nulls":6},"环境影响评价","不需办理","/","/","/"]
[{"$nulls":6},"初步设计及概算批复","不需办理","/","/","/"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021-12-01"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021-12-01"]
[2,"建筑工业化智能科技园",null,null,"以建筑工业核心技术+智慧智造，打造建筑产业一体化智慧科技园起步区，远期拓展提升打造大湾区建筑工业智慧产业集群。首期610亩，以国家装配式建筑产业基地、国家装配式建筑质量监督检验中心、国家绿色建筑质量监督检验中心等为核心基础，集聚建设地下空间装配式等智慧智造基地，省绿建、建筑工业化工程技术研究中心等",202000,"规划选址和用地预审","未完成","市自然资源局清城分局","推进落实","2021-12-01","广东省建筑工程集团有限公司","飞来峡镇","飞来峡镇","省前期"]
[{"$nulls":6},"用林手续","未完成","市林业局清城分局","积极推进","2022-03-01"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","不需办理","/","/","/"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","积极推进","2022-03-01"]
[{"$nulls":6},"环境影响评价","不需办理","/","/","/"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2022-03-31"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","积极推进","2022-07-31"]
[3,"大湾区现代家禽产业园",null,null,"规划建设精深加工、生鲜交易、文旅科创三大功能区，涉及家禽初级工、精加工、深加工、冷链物流、实体交易市场、线上电子交易市场、农业总部、农业科技研发、清远鸡及清远优质农产品博物馆等家禽业二三产环节，建成后将实现年加工量3亿只家禽，市场年交易额100~200亿元，年交易量10亿只家禽产品",300000,"规划选址和用地预审","未完成","市自然资源局清城分局","正在办理中","2021-12-30","清远清农电商有限公司","区农业农村局","清远市","省前期"]
[{"$nulls":6},"用林手续","未完成","市林业局清城分局","正在办理中","2021-12-30"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","正在办理中","2021-05-31"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","正在办理中","2021-05-31"]
[{"$nulls":6},"环境影响评价","不需办理","/","/","/"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021-05-31"]
[{"$nulls":6},"节能评估和审查","不需办理","/","/","/"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","计划2022年完成","2022-05-31"]
[4,"广东（清远）博宏药业有限公司总部经济建设项目","2020-441802-27-03-105364",null,"建筑面积18.8万平方米，建设总部大楼项目，包含管理员工办公，研发中心等。",54300,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","广东博宏健康产业科技有限公司","东城街办","二、清远市清城区东城街道华南声谷项目范围内","省前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","已完成","市自然资源局清城分局","/","/"]
[{"$nulls":6},"环境影响评价","不需办理","/","/","/"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","预计10月份中旬完成"]
[{"$nulls":6},"节能评估和审查","不需办理","/","/","/"]
[{"$nulls":6},"施工许可","未完成","清远市自然资源局清城分局","争取完成","预计11月份中旬完成"]
[5,"清远华清循环经济绿色科技创业园项目","91441802771879308B",null,"引进200家以循环经济为主题、绿色科技为基础的中小微企业入驻，培育创业主体，推进全民创业，全力打造优质孵化器，助力创新型绿色科技企业持续健康发展。",380000,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","清远华清再生资源有限公司","石角镇","石角镇","省前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","已完成","市自然资源局清城分局","/","/"]
[{"$nulls":6},"环境影响评价","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[6,"清远南方建材卫浴有限公司新中源跨境电商物流产业园新建项目","2107-441802-04-01-498874",null,"总用地面积约991.4亩，总建筑面积约752135平方米，主要建设内容包括仓储物流园区建设、仓库、分拨中心、综合楼及其他配套设施等。",420000,"规划选址和用地预审","不需办理","/","/","/","清远南方建材卫浴有限公司","源潭镇","源潭镇","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","不需办理","/","/","/"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成",2021]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","不需办理","/","/","/"]
[{"$nulls":6},"节能评估和审查","不需办理","/","/","/"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[7,"清远市进兴精密机械有限公司清远市清城区石角镇德龙大道旁地块项目（暂命名）厂区",null,null,"项目规划用地面积99967.88平方米，基地面积39021.08平方米，总建筑面积249553.76平方米，其中生产车间总建筑面积225802平方米。",112800,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","清远市进兴精密机械有限公司","石角镇","石角镇","省前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","已完成","市自然资源局清城分局","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[8,"清远市清城区顺农投资开发有限公司广东省清远市清城区现代农业产业园新建项目","2106-441802-04-01-297640",null,"到2023年，清远麻鸡原种鸡达到15万只，祖代种鸡达到30万套，父母代达到300万套，年出栏种苗2.5—3亿只。产业园总产值达到78.86亿元，带动产业园清远麻鸡标准化养殖率达到60%，肉鸡出栏量达到0.4亿羽以上。",181000,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成","2021年底","清远市清城区顺农投资开发有限公司、广东天农食品集团股份有限公司、清远市凤翔麻鸡发展有限公司、清远清农电商有限公司等","区农业农村局","清远市清城区飞来峡镇、源潭镇、龙塘镇、石角镇、横荷街道","市前期"]
[{"$nulls":6},"用林手续","未完成","市林业局清城分局","争取完成","2021年底"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021年底"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021年底"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021年底"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021年底"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021年底"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021年底"]
[9,"（豪美）高端节能系统门窗幕墙生产基地建设项目",null,null,"项目主要从事研发、设计、生产高性能环保节能的门窗和幕墙产品。",200000,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","豪美新材有限公司","石角镇","石角镇","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021-12-01"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[10,"东莞市德诚精密拉链科技有限公司年产2亿条拉链及上下游周边产业链项目",null,null,"主要生产制造尼龙拉链、金属拉链、塑料拉链，产量每年约2亿条",25000,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","东莞市德诚精密拉链科技有限公司","石角镇","石角镇","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","已完成","市自然资源局清城分局","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[11,"熙霖环保设备研发生产项目一期","2018-441802-50-03-003224",null,"  项目总用地面积43160.21平方米，规划总建筑面积为87639.57平方米，其中办公楼1栋：24567.74平方米；研发厂房3栋：35682.06平方米；员工宿舍3栋：26070.62平方米，架空层：1319.15平方米。主要经营环保设备研发、生产及销售、废活性炭年10万吨回收、处理及销售，设备年产量2100套，年产值达3.5亿元\n建筑面积：87639.58平方米    占地面积：43160.21平方米",21000,"规划选址和用地预审","不需办理","/","/","/","清远市熙霖节能环保工程咨询服务有限公司","源潭镇","源潭镇新田村","市前期"]
[{"$nulls":6},"用林手续","未完成","市林业局清城分局","争取完成","2021"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021"]
[12,"清远市嘉福创新产业园建设项目",null,null,"建设内容包括：中小企业总部及创新服务主楼、孵化器加速器及创新副楼及其生活配套设施。项目主要从事中小企业总部基地，众创空间+创业苗圃、孵化器、科创平台的建设与运营。",30400,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","广东嘉福创新投资有限公司","东城街办","东城街道","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","已完成","市自然资源局清城分局","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","不需办理","/","/","/"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[13,"中国联通（华南）智能通信互联网产业园项目",null,null,"拟建的中国联通集团公司（华南）智能通信互联网产业园区包含中国联通集团公司（华南）互联网人工智能服务中心、中国联通软件研究院广州分院、物联网及云服务中心、中国联通 BPO 产业示范基地、电子商务物流服务中心、清远生产管理楼，清远通信机房楼。",80000,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成","2021-12-01","中国联通集团公司","东城街办","东城街道","市前期"]
[{"$nulls":6},"用林手续","未完成","市林业局清城分局","争取完成","2021-12-01"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成",2021]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[14,"中伦综合体项目",null,null,"项目主要打造三大板块：一是打造中英经贸合作平台。重点发展展览贸易、跨境电商平台和国际贸易服务中心等。二是打造高端科技创新研发平台。计划引进汽车发动机项目公司、英国剑桥大学制造研究中心（IFM）、诺迈士科技研究中心及万达金融投资集团等。三是打造国际人才引进及教育服务平台。导入英国的先进科创资源，打造高端科研氛围，拟引入全英华人教授协会等。占地面积572亩。",500000,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","英中集团","石角镇","石角镇","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021-12-01"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[15,"广东得凯士运动科技有限公司项目",null,null,"主要生产高端军用、民用眼镜，年产量超400万副。",26700,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","广东得凯士运动科技有限公司","石角镇","石角镇","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","已完成","市自然资源局清城分局","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[16,"清远华鸿铜业有限公司二期项目",null,null,"占地950亩，其中，铜合金新材料加工片区占地300亩；新型新材料铝合金型材及高端品牌专用铝合金展柜加工片区占地350亩；新材料产业孵化器和孵化加速器片区占地250亩；总部大楼及新材料研发中心片区及生活辅助片区占地50亩。",400000,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","清远华鸿铜业有限公司","石角镇","石角镇","市前期"]
[{"$nulls":6},"用林手续","未完成","市林业局清城分局","争取完成","2021-12-01"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021-12-01"]
[{"$nulls":6},"环境影响评价","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"节能评估和审查","已完成","清远市发展和改革局","/","/"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021-12-01"]
[17,"清远市钛美铝业有限公司二期工程项目","未办理",null,"工程占地面积约47520平方米，规划建设成集生产车间、仓库、综合办公楼、宿舍楼为一体的围绕加工生产汽车零部件、电子电器等铝制品工业材的厂房及其配套建筑。",11000,"规划选址和用地预审","不需办理","/","/","/","清远市钛美铝业有限公司","源潭镇","源潭镇新马村委会、大连村委会","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2020"]
[{"$nulls":6},"用地报批","已完成","市自然资源局清城分局","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021-12-01"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021"]
[18,"城际清远源潭综合物流产业园项目","2018-441802-59-03-810020",null,"项目一期占地263.98亩，总建筑面积106002㎡。拟建设以汽车贸易、电商金融和贸易O2O综合服务为主的现代化综合服务型平台，不涉及跨境业务。主要建筑物包括5栋仓库及其配套的工具间、门卫及其他相关配套设施等。",53000,"规划选址和用地预审","不需办理","/","/","/","清远市安清信息科技发展有限公司","源潭镇","源潭镇秀溪村","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","不需办理","/","/","/"]
[{"$nulls":6},"环境影响评价","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"初步设计及概算批复","不需办理","/","/","/"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021.12]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021.12]
[19,"忠信（清远)光伏材料科技有限公司二期项目",null,null,"本项目二期规划建设用地面积为17970.92㎡，主要建设新增年产8000吨PVB胶片（聚乙烯醇缩丁醛膜）生产线。",21000,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","忠信（清远)光伏材料科技有限公司","石角镇","石角镇","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","已完成","市自然资源局清城分局","/","/"]
[{"$nulls":6},"环境影响评价","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[20,"广东江夏生态建设有限公司总部大厦项目","2103-441802-04-01-801858",null,"本项目规划总用地面积为12543.91平方米，总建筑面积为46373.56平方米,主要建设总部大厦主楼（约11 层）、四面裙楼及两层地下停车场。",28400,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","广东江夏生态建设有限公司总部大厦项目","横荷街办","横荷街","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","已完成","市自然资源局清城分局","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021.12]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021.12]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021.12]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021.12]
[21,"绿色环保板式家具及材料生产项目","2103-441802-04-01-961445",null,"项目总投资8500万元人民币，建筑总面积：25653.79平方米，占地面积：5032平方米，本项目从事木质板式家具（衣柜、书柜定制产品等）的生产，年产量15000套。","8500","规划选址和用地预审","不需办理","/","/","/","广东卡诺亚家居有限公司","源潭镇","源潭镇","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","不需办理","/","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021.12]
[{"$nulls":6},"初步设计及概算批复","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021.12]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021.12]
[22,"清远市清城区龙塘镇卫生院新院建设项目","2014-441802-84-01-003601",null,"项目总用地面积约20.24亩，规划总建筑面积为22117.82平方米，主要建设地下室、综合楼、后勤楼、医技楼、垃圾站及污水处理站。",12800,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成","2022","龙塘镇人民政府","龙塘镇","龙塘镇","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2022"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2022"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2022"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2022"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2022"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2022"]
[23,"清远市公安局清城分局业务技术大楼和警务技能训练基地项目","2020-441802-92-01-009247",null,"业务技术用房建设内容：指挥中心用房、办案用房、窗口用房、信息通信用房、网络安全保卫用房、机要工作用房、刑事技术用房、物证以及收缴物品保管用房、警用装备物资（含应急储备物资）库、警务技能训练用房、备勤用房、档案用房及道路、绿地、停车场、室外警察体训操场、智慧新网安、智慧新情指等；建设规模：12954.9平方米。\n训练基地建设内容：教学用房（含教室、警用装备仪器设备教学训练室、图书馆等）、行政用房、民警实战训练所需的训练用房（含泅渡馆、射击馆、擒拿格斗训练馆、模拟街区等）、学员宿舍、食堂及附属用房、智慧新警队等；建设规模：10770平方米。",18181,"规划选址和用地预审","不需办理","/","/","/","清远市公安局清城分局","清远市公安局清城分局","清远市清城区","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成",2021]
[{"$nulls":6},"环境影响评价","不需办理","/","/","/"]
[{"$nulls":6},"初步设计及概算批复","不需办理","/","/","/"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[24,"清城区社会福利中心建设项目","2020-441802-92-01-009095",null,"容积率1.5，计容建筑面积34710平方米，建筑密度35%，建筑基底面积8099平方米，绿地率30%，绿地面积6942平方米，地上建筑限高30米。2021年启动，完善相关规划、资料落实、招投标工程； \n2021年儿童抚育主体建筑、老人托养机构主体建筑完成70%以上；\n2022年儿童抚育主体建筑及老人托养主体建筑完成全面建设，完成装修、完成设施配套、完成绿化。",32000,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成",2021,"清城区民政局","清城区民政局","清城区东城街华南声谷北侧","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成",2021]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[25,"清远市清城区粮食储备库新库建设工程项目（一期）","2020-441802-59-01-009183",null,"规划建成集粮油储备、粮食应急加工、军粮供应、应急物资储备于一体的现代粮食和物资储备库。首期拟建设6万吨仓容的散装平房仓、1000吨植物油库、10000吨低温应急大米储存库、救灾物资库等设施。",35000,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成",2021.12,"清远市清城区粮食和物资储备有限公司","清城区发展和改革局","清城区飞来峡镇","市前期"]
[{"$nulls":6},"用林手续","未完成","市林业局清城分局","争取完成",2021.12]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成",2021.12]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成",2021.12]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021.12]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021.12]
[{"$nulls":6},"节能评估和审查","不需办理","/","/","/"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021.12]
[26,"天子山旅游度假区","2016-441802-61-03-011580",null,"项目总面积12000亩，建设用地面积601亩的生态旅游度假村",52000,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成","2021年底","清远晟冠君投资有限公司","飞来峡镇","清远市清城区飞来峡镇西坑村委","市前期"]
[{"$nulls":6},"用林手续","未完成","市林业局清城分局","争取完成","2021年底"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021年底"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021年底"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021年底"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021年底"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021年底"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021年底"]
[27,"文洞河生态旅游度假区项目",null,null,"文洞河生态水上乐园现状主要由3200亩水面、路堤和防护林构成，目前路堤为土质路面。规划将其路面适当进行改造建成绿道，另一方面是环形生态休闲漫步带，高空极速、综合拓展、探险漂流带",90000,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","广东云洞河旅游投资发展有限公司","飞来峡镇","清城区飞来峡镇文洞村委会","市前期"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021"]
[28,"九融汇金融产业集群创新服务基地建设项目",null,null,"在金融、EPE投资 、金融创新科技产业 等方面的 投资 优势，在清远互联网+ + 创新产业园投资 九融汇金融产业集群创新基地 ，通过引入金融 及金融科技创新 及服务企业 ，推动清远金融产业创新集聚，形成浓厚的金融产业氛围，服务和促进当地社会经济发展。",27000,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成","2021-12-01","九融汇（广州）产业园投资有限公司. ","东城街办","东城街道"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成",2021]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[29,"古城御品",null,null,"在清城区松岗路1号（原松岗客运站），总共土地面积7683.95平方米，该项目主楼一共有23层左右，地下负一层、负二层用作停车用途；首层、二层作为商场使用；三层至二十一层作为公寓式酒店使用；楼顶最后两层作为旋转餐厅使用。",20000,"规划选址和用地预审","不需办理","/","/","/","古城社区居委会","凤城街办","凤城街道"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","不需办理","/","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"节能评估和审查","不需办理","/","/","/"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[30,"松岗路停车楼",null,null,"原清城区松岗路清远市汽车站，面积约10000平方米，计划建设5层楼层式停车楼，首层作为肉菜市场使用，二层以上作为停车场使用。",4500,"规划选址和用地预审","不需办理","/","/","/","古城社区居委会","凤城街办","凤城街道"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"用地报批","不需办理","/","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","不需办理","/","/","/"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[31,"古朴风情旅馆街",null,null,"原清城区松岗路清远市汽车站周边，计划将该地段的旅馆旅业做一个整合，进行整体风格的改造翻新，打造成一条全新的古朴风情旅馆街。",1500,"规划选址和用地预审","不需办理","/","/","/","古城社区居委会","凤城街办","凤城街道"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"用地报批","不需办理","/","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"节能评估和审查","不需办理","/","/","/"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021-12-01"]
[32,"清城区第五幼儿园建设项目","2020-441802-47-01-022742",null,"项目占地约3332平方米（约合5.0亩），规划建筑面积约3600平方米，办园规模为12个班、360个幼儿学位。",2800,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成","2021","清城区教育局","区教育局","清远市清城区东城街道莲塘村委会凯旋村"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021"]
[33,"清远市中宿乡村休闲庄园项目",null,null,"在保护原生态山地环境及乡村特色的基础上，充分利用生态园的自然景观，形成“可览、可游、可居”的环境景观和集“自然一避暑一休闲一度假一康养一教育”于一体的乡村休闲庄园项目，发展体验乡村与森林旅游相结合的特色旅游。",100000,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","中宿投资有限公司","飞来峡镇","清城区飞来峡镇旧岭村委会"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021"]
[34,"清远市清城区人民法院审判综合大楼项目","无",null,"项目名称：清远市清城区人民法院审判综合大楼\n\n建设内容及规模：建筑面积为12980平方米，用地总面积约30亩，布局上主要以审判法庭为中心，与办公用房一并统筹建设。拟建设立案用房、审判用房、执行用房、信访接待用房、审判配套用房、审判信息管理用房、诉讼档案用房、司法警察警务用房、辅助用房九类功能用房。",9240,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成","2021-2025","清远市清城区人民法院","清远市清城区人民法院","清远市清城区"]
[{"$nulls":6},"用林手续","未完成","市林业局清城分局","争取完成","2021-2025"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021-2025"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021-2025"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021-2025"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021-2025"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021-2025"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021-2025"]
[35,"清城区洲心街伦洲岛片区截污管网及污水处理工程","2019-441802-49-01-049268",null,"拟建设一座污水处理站，铺设污水管网收集学地、联屋、新刘、旧刘、覃屋五村的污水进行处理。主要工程量为：建设污水处理站1座（处理规模为350m³/d）；截污管道铺设约6.3公里（DN250支截污管长度3.7公里，DN400主截污管长度2.6公里），建设检查井约280座，提升泵站1座。",1500,"规划选址和用地预审","不需办理","/","/","/","洲心街道办事处","洲心街办","清城区洲心街伦洲岛"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","已完成","清城区行政审批局","/","/"]
[{"$nulls":6},"用地报批","不需办理","/","/","/"]
[{"$nulls":6},"环境影响评价","不需办理","/","/","/"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"节能评估和审查","不需办理","/","/","/"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021-12-01"]
[36,"龙塘镇第一初级中学新建教学楼和师生\n饭堂工程项目","2020-441802-47-01-009015",null,"在龙塘一中新建1幢6000平方米综合教学楼，增加20个班，1000个学位；新建1幢师生饭堂。",12800,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成","2021-12-01","清城区龙塘镇人民政府","龙塘镇","清城区龙塘镇"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021-12-01"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021-12-01"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021-12-01"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021-12-01"]
[37,"广东雄星新材料有限公司7万平方米厂房建设项目","2020-441802-47-03-083547",null,"项目总建筑面积7万平方米，规划建设2个厂房，1个生产车间。",10000,"规划选址和用地预审","已完成","市自然资源局清城分局","/","/","广州市雄星塑料制品有限公司","源潭镇","源潭镇积余村"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"用地报批","不需办理","/","/","/"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[38,"远光电缆产业基地转型升级搬迁项目","暂无",null,"建设内容包括：销售及办公楼、研发及质检中心、饭堂/宿舍、特种导线车间、低压车间及布电线车间、高分子车间、铜导体及交联电缆车间、铝导线车间、熔轧车间、仓库、新能源电缆车间、总配电间、盘具车间等设施。",87000,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成",2021,"广东远光电缆实业有限公司","横荷街办","横荷街道"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成",2021]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[39,"清远市万安食品有限公司大型现代化屠宰厂改扩建项目","暂无",null,"项目用地面积51.34亩，计划建设猪、牛、羊待宰、屠宰、分割车间、低温冷藏库20000吨、食品集中加工中心、污水处理站、综合楼。",13000,"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成",2021,"清远市万安食品有限公司","横荷街办","清远市清三公路与北江水利枢纽工程施工便道交叉口西北角"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成",2021]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成",2021]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成",2021]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成",2021]
[40,"飞来峡镇社岗S252线拓宽工程",null,null,"本项目为省道S252线佛冈至清城中的一段，路线起点位于省道S252线与县道X376线相交处，路线整体基本自东向西走向，经佛冈县下迳、生产街、秧坎嘴村、清城区榨油岭村、社岗村、犁头咀，终点位于清城区飞来峡镇S252线与国道G240（银英公路）相交。",{"v":8934.69,"d":"8935"},"规划选址和用地预审","未完成","市自然资源局清城分局","争取完成","2021","清远市公路勘察规划设计院","飞来峡镇","清城区飞来峡镇社岗村委会"]
[{"$nulls":6},"用林手续","不需办理","/","/","/"]
[{"$nulls":6},"用海手续","不需办理","/","/","/"]
[{"$nulls":6},"可行性研究报告（申请报告、备案证）","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"用地报批","未完成","市自然资源局清城分局","争取完成","2021"]
[{"$nulls":6},"环境影响评价","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"初步设计及概算批复","未完成","清城区行政审批局","争取完成","2021"]
[{"$nulls":6},"节能评估和审查","未完成","清远市发展和改革局","争取完成","2021"]
[{"$nulls":6},"施工许可","未完成","清城区行政审批局","争取完成","2021"]